## Slide 1: Presentation to: CEAM 2013 Streamlining Environmental Compliance for Major Infrastructure Projects
September 19, 2013

## Slide 2: Environmental Impacts & Compliance
Best practices for environmental compliance for major infrastructure projects
Planning phase, design phase and construction phase.
Setting projects up for success.

## Slide 3: Introduction
Major infrastructure projects often necessitate unavoidable impacts to sensitive resources
  wetlands, waterways, forests
Early assessment of resources, and understanding of regulatory requirements reduces permit approval time and unexpected requirements

## Slide 4: Introduction
Discuss best practices for incorporating environmental compliance into design, permitting, construction
Example of best practices implemented on I-95 Express Toll LanesSM project
Traditional permitting approach vs. streamlined approach using best practices

## Slide 5: Permitting Approaches
Traditional Approach
  Submit at SF or Final Design
  Permit issued at back end of design, right before construction
Streamlined Approach Utilizing Best Practices
  Submit at Concept Design
  Permit issued around SF or Final Design
  Special conditions incorporated into final design
  Implemented on I-95 Express Toll Lanes, Intercounty Connector (MD 200), and other major infrastructure projects
Notes: 5

## Slide 6: Pitfalls/Disadvantages of Traditional Approach
Regulatory agencies typically not involved until application submitted
Review  permit issuance
  9 – 12 months
  Back end of design
Agency feedback may require design revisions late in the game, further impacting schedule and budget.
Agencies are not “part” of the design process, not fostering teaming and trust

## Slide 7: Pitfalls/Disadvantages of Traditional Approach
Holds up construction on major projects with
with multiple contracts/task orders with different schedules
  Permit application held up until all contracts/task orders reach permittable stage (e.g., SF or Final Design)
  Construction cannot begin until permits covering entire project area are issued
Cannot permit individual contracts/task orders separately

## Slide 8: Best Practices For Environmental Compliance

## Slide 9: Best Practices
Know your client and previous agreements
  MOAs, MOUs, exemptions under regulations
  Don’t rely on regulators to identify these
Know the regulations and requirements for permit
  Understand documentation required – get it right the first time!
  COMAR is a great resource
  When in doubt, contact the agencies – they’re there to help!
Identify environmental resources at planning stage
  Plan study areas conservatively
  Reduce need for additional studies as design progresses

## Slide 10: Best Practices
Include Avoidance & Minimization in design
  Reduce impacts to only those unavoidable
  More impacts = More regulatory review/permitting = More money and time
Like infrastructure, water resources are assets
  Avoiding/minimizing impacts saves money (no/less mitigation)
  Provide ecological, recreational, aesthetic value

## Slide 11: Best Practices
Communication, Teaming, Build Trust
  Involve the agencies early and often
  Include them in the process and be transparent
    Don’t stockpile information
    Communicate your needs, schedules, etc.
    Be willing to identify potential problems/concerns and ask questions
    Cultivate them as partners, not adversaries
Building trust reduces review times and improves flexibility

## Slide 12: Best Practices
Team with the agencies
  Use agencies as a resource to help navigate permitting environment
  Agencies want project to be successful and go smoothly
    Especially infrastructure projects improving public health and safety
    Realize agencies’ agendas are different from, but not necessarily opposed, to yours
    Successful and smooth-running projects = less work for the agencies, who are already overloaded

## Slide 13: Best Practices
Submit permit at Concept Design based on
worst case scenario of impacts for LEDPA
  Complete resource assessments during planning stage
  Begins permitting process early and concurrent with design
  Permits issued with conditions to continue avoidance & minimization during design, including possible design requirements
  Agencies are “part” of the design process
    Review designs for compliance
    Work with applicant to resolve issues during design
  Final designs with agency approval move straight to procurement and construction, rather than waiting for permitting process
Notes: 13

## Slide 14: Best Practices
Pursue project-wide permit for major projects
with multiple contracts/task orders
  One public notice
  Construction of early contracts/task orders doesn’t have to wait for later contracts
Transparency and communication of changes to impacts during final design and construction
  Unavoidable increases to permitted impacts will very likely occur during final design – agencies need to accept “fact of life”
  Flag these to agencies when submitting plans, include justification
  Involve agencies in discussions of field mods increasing impacts
  Report design and construction impacts on regular basis (e.g., quarterly)

## Slide 15: Best Practices
Establish an Environmental Lead
  Lead design reviews for compliance
  Track and report compliance with permits and conditions
  Serve as single point-of-contact with agencies
Establish an Environmental Monitor
  Inspect, ensure, and report on environmental compliance during construction
  Identify potential compliance issues early, before non-compliance or violation occurs
  Team with other inspectors, engineers, and managers to problem-solve issues

## Slide 16: I-95 Express Toll LanesSM (ETLs) Project

## Slide 17: I-95 ETLs Project - Background
MDTA currently designing and constructing improvements to I-95
  Permitted for 10 miles of I-95 from I-95/I-895 North split to ~3 miles north of White Marsh Blvd (MD 43)
  Adding general purpose and managed access (Express Toll Lanes) to improve safety and service
  Reconstruction of intersections at I-895, I-695, MD 43
Ten individual construction contracts
Planning/NEPA phase, culminating with FONSI in July 2005
Design began shortly after with construction of first contract beginning 2005, tenth and final contract currently in procurement.

## Slide 18: I-95 ETLs Project - Background

## Slide 19: I-95 ETLs Project - Background

## Slide 20: I-95 ETLs Project – Best Practices
Planning and Permitting Phases
  Wetlands and Waterways
    Wetlands and waterways delineated, JD field visits with USACE completed, during Planning/NEPA phase
    USACE involved during Planning/NEPA phase design
      Provided input on design/impacts
      Other environmental commitments included in FONSI
    Permit application and permits issued based on impacts associated with PI design included in FONSI
    Both USACE and MDE included Special Conditions for design, construction, and post-construction

## Slide 21: I-95 ETLs Project – Best Practices
Planning and Permitting Phases
  Forests
    Project subject to Reforestation Law
      Requires 1:1, acre for acre mitigation
      Accounts for forests and individual trees
      Reforestation credit granted for forests and individual trees
      Reforestation needs to be in ground 1 year or 2 growing seasons after project completion
    No project-wide approval
    DNR preferred to review and permit impacts contract by contract
    Forest stands delineated during Planning/NEPA phase
Notes: 21

## Slide 22: I-95 ETLs Project – Best Practices
Detailed Design Phase
  Environmental Lead established
    Review designs for compliance
    Manage environmental permits
    Track and report compliance with permits, conditions, and commitments
    Serve as single point-of-contact with agencies

## Slide 23: I-95 ETLs Project – Best Practices
Detailed Design Phase
  Wetlands and Waterways
    MDTA, Discipline Leads (e.g., Environmental Lead), and agencies performed concurrent reviews
    Environmental Lead and Agencies reviewed and commented on compliance and avoidance & minimization
    Designer addressed comments during development of subsequent design submittal
    After all agency comments addressed, MDE issued approval letter, USACE issued email stating no further comments

## Slide 24: I-95 ETLs Project – Best Practices
Detailed Design Phase
  Forests
    Planting Plans reviewed at each design phase to ensure plantings meet Reforestation Law requirements
    Reforestation Law review (application and forest impact plates) submitted based on SF Design
    Reforestation/Planting Plans submitted 90 days prior to Advertisement
    Approval for each contract issued prior to Advertisement
    Off-site mitigation search conducted and several sites selected

## Slide 25: I-95 ETLs Project – Best Practices
Detailed Design Phase
  Communication with Agencies
    Environmental Lead flagged any increase in impacts to individual resources and provided justification to agencies
    Agreement made to avoid multiple permit modifications
      Agency approval letter/email of final design plans authorized all increases to individual resources above permitted level
      One permit modification at end of design will align permit with final design impacts
    Agencies involved throughout entire detailed design
    Quarterly impact updates
    Quarterly meetings
    Regular emails, phone calls, other ad-hoc meetings
Notes: 25

## Slide 26: I-95 ETLs Project – Best Practices
Construction Phase
  Wetlands and Waterways
    Agencies part of redline review process
    MDTA provides Environmental Construction staff
    Per permit conditions, MDTA funds Independent Environmental Monitor
    All construction staff, inspectors, and IEM work together to identify problems early and resolve issues
    Quarterly meetings
    Feedback re: construction issues in field during early contracts informed design for later contracts
    Environmental Construction Inspectors prepare daily reports. IEM prepares daily and monthly reports

## Slide 27: I-95 ETLs Project – Best Practices
Construction Phase
  Forests
    If impacts changed due to redlines, then new Reforestation Law approval was issued by DNR
    Reforestation visited after installation and again at one year post installation
    Fee-in-lieu payment accepted to mitigate for remainder of required reforestation after on-site and off-site planting was maximized and documented in a report

## Slide 28: Improving Streamlined Approach
Ideas for improving streamlined approach
  Based on experience with I-95 ETL Project
  Assume all impacts within LOD to be permanent at permit application
  Puts worst case scenario on public notice, reducing risk of future public notice
  Requires buy-in from agencies
    Permanent impacts that may be avoidable/minimized are technically authorized

## Slide 29: Improving Streamlined Approach
Ideas for improving streamlined approach
  Pay careful attention to wetland and stream delineation efforts
    Ensure study areas are large enough to allow for changes in the project limits
    Ensure that all necessary information is collected at the beginning (functions and values, wetland and stream types)
    Careful tracking and QA of water resources and impacts so there is consistency among various documents (JPA, EA/FONSI, etc.)
  Consider beginning the permitting process in parallel with the NEPA efforts
  Integrate environmental and engineering functions within the design organization

## Slide 30
www.straughanenvironmental.com
Straughan Environmental, Inc.
10245 Old Columbia Road
Columbia, MD 21046
marketing@straughanenvironmental.com  301-362-9200